## Sheet1
Lean Six Sigma Project Charter
Project Name: | Reduction of Operator Error Non-Conformance on Example Line
Gaps/Issues /Problem Statement: | This team is formed to reduce the occcurence of operator error in the example area. Operator error is the leading reason cited in all Non-confromance notifications that were submitted in the previous 12 months. (50% of total).
Charter Ojective/ Goal | Reduce operator by 30% by the end of August.
Scope: | The teams focus is restricted to four types of operator area that when combined, represent 80% of all operator error NCNs.
Defect: | Operator error is defined in our exmaple information system by the cause description: operator error - 005.
Measures/ Deliverables: | 30% reduction in NCN caused by Operator Error as found in data extracted monthly from example information system. Cost of poor quality will be reduced by 0.05%.
Milestones | Stage | Start Date
| Define | 2020-03-12
| Measure | 2020-04-01
| Analyze | 2020-05-01
| Improve | 2020-05-20
| Control | 2020-07-01
Project Sponsor/ Champion: | Quality Assurance Manager and Master Black Belt
Date of Approval: | 2020-03-12
Project Completion Date: | 07/28/0202
Team Members: | Project Manager
Consultants
Production supervisors
Production operators
Manufacturing engineering
Project Budget: | < $5,000
Business Case: | A 30% reduction in operator error will yield a projected annual savings of $75.3k.
Document Revisions | Date | Description of Change | Person making change
| 2020-03-12 | Original releas | PM
| 5/1//2020 | Added business case | PM
| 2020-05-01 | Added operational defintions | PM